## Issues
ITEM# | ISSUE | DATE | DESCRIPTION | IMPACT | RAISED BY | RESPONSIBLE | STATUS | NOTES
I_01 | Don't know how to assign Manager and Scribe roles | 2019-09-12 | Need to determine who is doing what role when | High | Francisco | Francisco | Solved
I_02 | Need Technical Lead for Environment Setup | 2019-09-12
I_03 | Need someone in charge of Quality Assurance | 2019-09-12
I_04 | Problems in the installation of MySQL | 2019-09-16 | Solve the issue when the system install the correct version | High | Daniel | Daniel | Solved
I_05 | Difficulty defining test strategy requirements | 2019-09-19 |  | High | Ralph | Project Team | Solved
I_06 | Automated Tools use for security in Database | 2019-09-23 | Need to detemine what tools are going to use to test the security for the database | High | Francisco | Project Team | Solved
I_07 | Some details missed in the Test Strategy | Septmeber 24, 2019 | Missed Code Review, progress reports/Status Reports, static code analysis, prioritization of defects | High | Stakeholder Kim Gariepy | Project Team | Solved
I_08 | Limited time to complete all different types of testing | Septmeber 24, 2019 | Need to conduct Usability Testing, Functional Testing, Security Testing and Automated Testing in 2 weeks | Medium
I_09 | What Tools will be used for Static Code Analysis | 2019-09-26 | Need to know what tool will be use for the code review | Medium | Rose | Project Team | Solved
I_10 | Unclear on Boundaries for Boundary Value Analysis | 2019-10-03 | Need to know what limits there are on variable inputs | Medium | Francisco | Project Team | Solved
I_11 | Unclear on how to get started with Test Cases | 2019-10-03 |  | High | Daniel | Project Team | Solved
I_12 | Security Test Cases don't appear to fit in to any current Use Cases | 2019-10-12 | Need to figure out what Use Cases to match Security test cases to | High | Daniel | Project Team | Solved
I_13 | Team missed some Requirements for Passwords | 2019-10-14 | Team will need to update Test Cases to match the missed requirements | High | Rose | Project Team | Solved
I_14 | Conflict between sets of requirements regarding deletion of users | 2019-10-16 | Team needs to clarify deletion of users requirements with stakeholders | Medium | Lyan | Project Team Project Owner: Kim | Solved
I_15 | No max bus capacity provided in requirements | 2019-10-18 | Team needs to determine what the max bus capacity value should be | Medium | Mrinal | Project Team | Solved
I_16 | No max passengers that can be booked at once provided in requirements | 2019-10-19 | Team needs to determine what the max # of passengers that can be booked at once should be | Medium | Francisco | Project Team Project Owner: Kim | Solved
I-17 | It was discovered that the testing environment was not set up properly | 2019-11-02 | Team needs to fix testing environment before test execution begins | High | Ralph | Project Team | Solved
I_18 | Can't run any Administrator tests as Admin login not working | 2019-11-14 | Team needs to determine what to do with these test cases for now | High | Daniel | Project Team | Solved

## Actions
ITEM# | ITEM# ISSUE TAB | ACTION TAKEN | COMPLETION DATE | IMPACT | RESPONSIBLE | STATUS | NOTES
A_01 |  | Created Chart to Track Roles | 2019-09-12 | Medium | Francisco | Completed
A_02 |  | Created Rough Project Plan | 2019-09-12 | High | Dan | Completed
A_03 |  | Testing Environment Setup | 2019-09-12 | High | Dan | Completed
A_04 |  | Testing Environment Setup for new members | 2019-09-16 | High | Dan | Completed | All completed
A_05 |  | Update document for the role rotation | 2019-09-19 | Medium | Francisco | Completed
A_06 | I_05 | The team use waterfall model for testing approach | 2019-09-23 | High | Project team | Completed
A_07 | I_07 | The Team will update the Test Strategy, adding in missed information | 2019-09-30 | High | Project Team | Completed
A_08 | I_06 | The team download the wireshark and BSQL hacker tools for security of the database | 2019-09-26 | High | Project team | Ongoing
A_09 | I_10 | The team analyzed the SQL database and Requirements to determine variable boudnaries | 2019-10-03 | medium | Project Team | Completed
A_10 | I_12 | Team created new "Hacker" module to contain Abuse Cases which model Security risk scenarios | 2019-10-13 | High | Project team | Completed
A_10 | I_13 | The team updated Admin User Creation Test Cases to meet Password Requirements | 2019-10-16 | High | Project team | Completed
A_11 | I_14, I_16 | Team consulted Project Owner for requirements clarification | 2019-10-19 | Medium | Project team | Completed
A_12 | I_17 | Team discovered issue with SQL database setup | 2019-11-07 | High | Project Team | Completed

## Decisions
ITEM# | DATE | DESCRIPTION | IMPACT | ITEM# ISSUE TAB | NOTES
D_01 | 2019-09-12 | Role Rotation | High | I_01 | Francisco has created chart to track roles
D_02 | 2019-09-12 | Technical lead | High | I_02 | Dan will take on this role
D_03 | 2019-09-12 | Meeting Times | High |  | Meeting will be held Monday at 11am, Wednesday at 4pm and Thursdays at 6pm
D_04 | 2019-09-12 | Meeting Format | Medium |  | Meetings will be held in person
D_05 | 2019-09-12 | Quality Assurance Manager Role | Medium | I_03 | Quality Analyst will be assigned for each Milestone
D_06 | 2019-09-19 | Automated tools to use | High |  | Use Jmeter and Selenium as automated tools
D_07 | 2019-09-19 | Provide guideline steps in operating the Tools | High |  | Steps by step process in operating the ewheelz app
D_08 | 2019-09-20 | What Software development lifecycle will be use? | Medium | I_05 | The team decided to use waterfall model
D_09 | 2019-09-21 | Team will divide into sub-team to work on different types of testing | Medium | I_08 | Daniel, Anand, Mrinal doing Functional; Ralph and Lyan doing Heurisitic Evaluation; Francisco and Rose doing Automated and Security
D_10 | 2019-09-26 | Need to detemine what tools are going to use to test the security for the database | Hign | I_06 | The team decided to use wireshark for the security of the database
D_11 | 2019-10-03 | Team Reviewed Applicability of Code Review and Static Code Analysis | Low | I_09, I_07 | Team decided these tools were not applicable to this project
D_12 | 2019-10-03 | Team discussed use of Progress Reports and Status Reports | Low | I_07 | Team determined these reports would be utilized at later stages of the project
D_13 | 2019-10-03 | Team assessed Boundary Value Analysis sources | Medium | I_10 | Team determined that SQL database analysis would reveal variable boundaries
D_14 | 2019-10-03 | Team needed starting point for Test Cases | Medium | I_11 | Team determined that Use Cases would be created first which would in turn guide creation of test cases
D_15 | 2019-10-13 | Need Use cases that match with Security Test Cases | High | I_12 | Team will create new section in Use Cases for "Abuse Cases" which Security Test Cases will map to
D_16 | 2019-10-17 | Need to know requirements for deletion of users | Medium | I_14 | Stakeholders clarified that Admins should not be allowed to delete users as this could affect database maintenance, however Admins should be able to deactivate users
D_17 | 2019-10-18 | Need to decide on max capacity for Busses | Medium | I_15 | Based on research team determined maximum value for the criteria should be 300
D_18 | 2019-10-19 | Need to know max # of passengers that can be booked at once | Medium | I_16 | Team consulted with Project Owner and received requirement clarification. Max number of passengers at once = 16
D_19 | 2019-11-06 | Team needs to determine how to split up testing phases | Medium |  | Team has decided each phase of testing will last one week
D_20 | 2019-11-14 | Can't run Admin test cases | High | I_18 | Team decided to mark these test cases down as "Blocked" for now

## Risks
RISK# | RISK DESCRIPTION | Primary Effect | Probability (High/Medium/Low) | Risk Impact (High/Medium/Low) | Trigger | MITIGATION PLAN | CONTINGENCY PLAN | STATUS
R_01 | Security Issue Missed | Quality | Medium | High | Security Testing not Adequately thorough | Design Security Testing around Industry Standards | have team ready to role out quick patches if security issues are identified after release | Future
R_02 | Scope Need to be Updated | Cost/Schedule | Low | High | Defect revealed where the resolution requires an adjustment to the scope | Developers match Development Plan to Requirements | Cost and or Schedule will have to be adjusted to account for increased size of scope | Ongoing
R_03 | Needed Software becomes Obsolete | Schedule/Quality/Scope | High | High | Flash Player is being discontinued in the near future | Development team designs components to work in multiple technologies | Will have to update components to work in javaScript or something else other than flash | Ongoing
R_04 | Hackers use SQL injections to access private data | Quality | Medium | High | Hackers enter SQL Injection statements into data entry fields | Data intake designed to catch SQL Injection statements and prevent the, | SQL Database designed with parameterized queries rather than dynamic queries to prevent any SQL injections that get through from doing any damage | Ongoing
R_05 | Testing goes over scheduled time | Schedule/Scope | Medium | Medium | Testing plan underestimates required time to accomplish tasks | Team thoroughly documents Test Plan and Test Cases to ensure testing is on schedule. Team automates Functional tests so that regression testing can be done very quickly | Team has prioritized tests so that those that are less important can be set aside for the more important ones to keep testing on schedule | Ongoing
R_06 | Hackers utilize Ddos attack to break system and steal data | Quality/Cost | Medium | High | Hackers identify potential weakness in system and exploit it | Stress testing performed to ensure system can handle greater than expected traffic. Security measures in place to identify malicious behaviour and cut off the source | If Ddos attack can not be stopped, System will shut itself down to prevent attackers from accessing private data | Ongoing
R_07 | Testing team misses a System breaking issue | Quality | Low | High | User utilizes a function that was not properly tested resulting in a system crash | Team thoroughly designs Use Cases to ensure all potential scenarios have been covered and maps all test cases back to Use Cases to ensure integrity | Failover and Recovery systems/plans in place to fix the system if any catastrophic issue occurs | Ongoing
R_08 | Test Cases do not provide full requirements coverage | Quality | Low | Low | Team concludes testing without having achieved full coverage | Team thoroughly inspects requirements and Creates use Cases to cover all requirements and Creates Test Cases to cover every possible flow of Use Cases and maps back all Test Cases to corresponding Use Cases ensuring requirements coverage | Teams Coverage should be at least good enough that resulting defect density is so low that any issues not covered are minor and nergligible | Ongoing
R_09 | Team identifies defects that are too large for Development team to properly address in alloted time | Schedule/Cost/Quality | Low | High | Team identifies a defect for which the resolution requires a massive overhaul of one or many system components | System requirements should be well formed and adhered to by development team | Stakeholders will have to approce schedule and budget extension in order to fix the issue or approve moving forward with a lower quality product | Ongoing
R_10 | Team falls behind testing schedule | Schedule/Cost | High | Medium | Not as many test cases are completed on a given day as planned | Team's test schedule designed in a thorough and feasible manner | Any missed test cases will have to be made up on the following day, even if overtime is required | Past
Note on C1: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Cost, Scope Schedule or Quality

## Team
INFO6068 | Capstone Project
Team Name: | Team Pro-Test
Members: | Daniel Gilbert
Mrinal Chopra
Lyan Joy Limjap
Francisco Gomez
Ralph Anonuevo
Rose Maria George
Anand Karithadathil Baby