## Summary - Phase 1
| Overall progress of the QA cycle(Ontime, delayed, Stopped) | On time
| Total number of test cases | 221
| Number of testers | 7
| Test cycle duration | 7 days
Status for 12/11/2019 |  |  | Overall status
|  |  |  | Number of test cases planned | 221
| Number of test cases planned | 40 |  | Number of test cases executed | 221
| Number of test cases executed | 40 |  | Pass Percentage of the defects | 94%
| Number of test cases executed overall | 40 |  | Defects density | 2 per day
| Number of defects encountered today | 5 |  | Critical defects percentage | 90%
| Number of defect encountered so far | 5
| Number of critical defects- still open | 3
Status for 13/11/2019
| Number of test cases planned | 30
| Number of test cases executed | 28
| Number of test cases executed overall | 68
| Number of defects encountered today | 4
| Number of defect encountered so far | 9
| Number of critical defects- still open | 9
Status for 14/11/2019
| Number of test cases planned | 40
| Number of test cases executed | 42
| Number of test cases executed overall | 110
| Number of defects encountered today | 2
| Number of defect encountered so far | 11
| Number of critical defects- still open | 11
Status for 15/11/2019
| Number of test cases planned | 30
| Number of test cases executed | 30
| Number of test cases executed overall | 140
| Number of defects encountered today | 2
| Number of defect encountered so far | 10
| Number of critical defects- still open | 10
Status for 16/11/2019
| Number of test cases planned | 30
| Number of test cases executed | 28
| Number of test cases executed overall | 168
| Number of defects encountered today | 2
| Number of defect encountered so far | 12
| Number of critical defects- still open | 12
Status for 17/11/2019
| Number of test cases planned | 30
| Number of test cases executed | 32
| Number of test cases executed overall | 200
| Number of defects encountered today | 2
| Number of defect encountered so far | 14
| Number of critical defects- still open | 14
Status for 18/11/2019
| Number of test cases planned | 21
| Number of test cases executed | 21
| Number of test cases executed overall | 221
| Number of defects encountered today | 0
| Number of defect encountered so far | 14
| Number of critical defects- still open | 14

## Summary - Phase 2
| Overall progress of the QA cycle(Ontime, delayed, Stopped) | On time
| Total number of test cases | 221
| Number of testers | 7
| Test cycle duration | 7 days
Status for 19/11/2019 |  |  | Overall status
|  |  |  | Number of test cases planned | 221
| Number of test cases planned | 40 |  | Number of test cases executed | 221
| Number of test cases executed | 40 |  | Pass Percentage of the defects | 85%
| Number of test cases executed overall | 40 |  | Defects density | 3.2 per day
| Number of defects encountered today | 5 |  | Critical defects percentage | 95%
| Number of defect encountered so far | 18
| Number of critical defects- still open | 18
Status for 20/11/2019
| Number of test cases planned | 30
| Number of test cases executed | 30
| Number of test cases executed overall | 70
| Number of defects encountered today | 4
| Number of defect encountered so far | 22
| Number of critical defects- still open | 22
Status for 21/11/2019
| Number of test cases planned | 40
| Number of test cases executed | 40
| Number of test cases executed overall | 110
| Number of defects encountered today | 2
| Number of defect encountered so far | 24
| Number of critical defects- still open | 24
Status for 22/11/2019
| Number of test cases planned | 30
| Number of test cases executed | 30
| Number of test cases executed overall | 140
| Number of defects encountered today | 2
| Number of defect encountered so far | 26
| Number of critical defects- still open | 26
Status for 23/11/2019
| Number of test cases planned | 30
| Number of test cases executed | 30
| Number of test cases executed overall | 170
| Number of defects encountered today | 2
| Number of defect encountered so far | 28
| Number of critical defects- still open | 28
Status for 24/11/2019
| Number of test cases planned | 30
| Number of test cases executed | 30
| Number of test cases executed overall | 200
| Number of defects encountered today | 2
| Number of defect encountered so far | 30
| Number of critical defects- still open | 30
Status for 25/11/2019
| Number of test cases planned | 21
| Number of test cases executed | 21
| Number of test cases executed overall | 221
| Number of defects encountered today | 2
| Number of defect encountered so far | 32
| Number of critical defects- still open | 32

## Detailed Status - Phase 1
Module | Test Case ID | Test Case | Complexity | Responsible tester | Date of Execution(Can be past, present or future date) | Status(Pass/Fail/blocked/not executed) | Defect ID- Brief description | Severity | Status
Functional Test Cases
User Module | TC_F_UL_01 | PositiveUserLogin |  | Mrinal | 2019-11-12 | Fail | F_001: Login button takes user directly to main page. Never prompted for credentials | High | Open
| TC_F_UL_02 | NegativeUserLogin |  | Mrinal | 2019-11-12 | Fail | F_001 | High | Open
| TC_F_UL_03 | NegativeUserLogin |  | Mrinal | 2019-11-12 | Fail | F_001 | High | Open
| TC_F_UL_04 | NegativeUserLogin |  | Mrinal | 2019-11-12 | Fail | F_001 | High | Open
| TC_F_UL_05 | ExceptionUserLogin |  | Mrinal | 2019-11-12 | Fail | F_001 | High | Open
| TC_F_UL_06 | PositiveUserLogout |  | Mrinal | 2019-11-12 | Blocked | F_001
| TC_F_UL_07 | NegativeUserLogout |  | Mrinal | 2019-11-12 | Blocked | F_001
| TC_F_UL_08 | NegativeUserLogout |  | Mrinal | 2019-11-12 | Blocked | F_001
| TC_F_UL_09 | ExceptionUserLogout |  | Mrinal | 2019-11-12 | Blocked | F_001
Routes Module | TC_F_VR_01 | PositiveViewRoute |  | Mrinal | 2019-11-12 | Pass
| TC_F_VR_02 | NegativeViewRoute |  | Mrinal | 2019-11-12 | Pass
| TC_F_VR_03 | ExceptionViewRoute |  | Mrinal | 2019-11-12 | Pass
| TC_F_VPP_01 | PositiveViewPickupPoints |  | Mrinal | 2019-11-12 | Pass
| TC_F_VPP_02 | NegativeViewPickupPoints |  | Mrinal | 2019-11-12 | Pass
| TC_F_VPP_03 | ExceptionViewPickupPoints |  | Mrinal | 2019-11-12 | Pass
Travels Module | TC_F_VT_01 | PositiveViewTravel |  | Mrinal | 2019-11-12 | Fail | F_002: Travels Button not present on page. Can't even get to Travel Agency Section | Low | Assigned
| TC_F_VT_02 | NegativeViewTravel |  | Mrinal | 2019-11-12 | Fail | F_002 | Low | Assigned
| TC_F_VT_03 | ExceptionViewTravel |  | Mrinal | 2019-11-12 | Fail | F_002 | Low | Assigned
Testimonials Module | TC_F_TE_01 | PositiveGiveTestimonial |  | Mrinal | 2019-11-12 | Pass
| TC_F_TE_02 | NegativeGiveTestimonial |  | Mrinal | 2019-11-12 | Pass
| TC_F_TE_03 | NegativeGiveTestimonial |  | Mrinal | 2019-11-12 | Pass
| TC_F_TE_04 | PositiveViewTestimonials |  | Mrinal | 2019-11-12 | Pass
Reservations Module | TC_F_BT_01 | NegativeBookTickets1 |  | Dan | 2019-11-13 | Fail | F_003: Can't select date and "Check Availability" button doesn't work | High | Assigned
| TC_F_BT_02 | NegativeBookTickets2 |  | Dan | 2019-11-13 | Fail | F_003 | High | Assigned
| TC_F_BT_03 | NegativeBookTickets3 |  | Dan | 2019-11-13 | Fail | F_003 | High | Assigned
| TC_F_BT_04 | NegativeBookTickets4 |  | Dan | 2019-11-13 | Fail | F_003 | High | Assigned
| TC_F_BT_05 | NegativeBookTickets5 |  | Dan | 2019-11-13 | Fail | F_003 | High | Assigned
| TC_F_BT_06 | NegativeBookTickets6 |  | Dan | 2019-11-13 | Fail | F_003 | High | Assigned
| TC_F_BT_07 | NegativeBookTickets7 |  | Dan | 2019-11-13 | Fail | F_003 | High | Assigned
| TC_F_BT_08 | PositiveBookTickets |  | Dan | 2019-11-13 | Fail | F_003 | High | Assigned
| TC_F_CT_01 | NegativeCancelTickets |  | Dan | 2019-11-13 | Pass
| TC_F_CT_02 | NegativeCancelTickets |  | Dan | 2019-11-13 | Pass
| TC_F_CT_03 | NegativeCancelTickets |  | Dan | 2019-11-13 | Pass
| TC_F_CT_04 | PositiveCancelTickets |  | Dan | 2019-11-13 | Fail | F_004: "Cancel" button after entering proper ID does not work | High | Assigned
Admin Module | TC_F_AML_01 | PositiveAdminLogin |  | Dan | 2019-11-14 | Fail | F_005: Admin login non functional | High | Assigned
| TC_F_AML_02 | NegativeAdminLogin |  | Dan | 2019-11-14 | Fail | F_005
| TC_F_AML_03 | NegativeAdminLogin |  | Dan | 2019-11-14 | Fail | F_005
| TC_F_AML_04 | NegativeAdminLogin |  | Dan | 2019-11-14 | Fail | F_005
| TC_F_AML_05 | NegativeAdminLogin |  | Dan | 2019-11-14 | Fail | F_005
| TC_F_AML_06 | PositiveAdminLogout |  | Dan | 2019-11-14 | Blocked | F_005
| TC_F_AML_07 | NegativeAdminLogout |  | Dan | 2019-11-14 | Blocked | F_005
| TC_F_AML_08 | NegativeAdminLogout |  | Dan | 2019-11-14 | Blocked | F_005
| TC_F_AML_09 | ExceptionAdminLogout |  | Dan | 2019-11-14 | Blocked | F_005
| TC_F_AML_10 | ResetAdminLogin |  | Dan | 2019-11-14 | Blocked | F_005
| TC_F_AMUC_01 | NegativeUserCreation1 |  | Dan | 2019-11-14 | Blocked | F_005
| TC_F_AMUC_02 | NegativeUserCreation2 |  | Dan | 2019-11-14 | Blocked | F_005
| TC_F_AMUC_03 | NegativeUserCreation3 |  | Dan | 2019-11-14 | Blocked | F_005
| TC_F_AMUC_04 | NegativeUserCreation4 |  | Dan | 2019-11-14 | Blocked | F_005
| TC_F_AMUC_05 | NegativeUserCreation5 |  | Dan | 2019-11-14 | Blocked | F_005
| TC_F_AMUC_06 | NegativeUserCreation6 |  | Dan | 2019-11-14 | Blocked | F_005
| TC_F_AMUC_07 | NegativeUserCreation7 |  | Dan | 2019-11-14 | Blocked | F_005
| TC_F_AMUC_08 | NegativeUserCreation8 |  | Dan | 2019-11-14 | Blocked | F_005
| TC_F_AMUC_09 | NegativeUserCreation9 |  | Dan | 2019-11-14 | Blocked | F_005
| TC_F_AMUC_10 | NegativeUserCreation10 |  | Dan | 2019-11-14 | Blocked | F_005
| TC_F_AMUC_11 | NegativeUserCreation11 |  | Dan | 2019-11-14 | Blocked | F_005
| TC_F_AMUC_12 | NegativeUserCreation12 |  | Dan | 2019-11-14 | Blocked | F_005
| TC_F_AMUC_13 | PositiveUserCreation1 |  | Dan | 2019-11-14 | Blocked | F_005
| TC_F_AMUC_14 | PositiveUserCreation2 |  | Dan | 2019-11-14 | Blocked | F_005
| TC_F_AMDU_01 | PositiveUserDeactivation |  | Dan | 2019-11-14 | Blocked | F_005
| TC_F_AMDU_02 | NegativeUserDeactivation1 |  | Dan | 2019-11-14 | Blocked | F_005
| TC_F_AMDU_03 | NegativeUserDeactivation2 |  | Dan | 2019-11-14 | Blocked | F_005
| TC_F_AMPC_01 | PositivePasswordChange |  | Dan | 2019-11-14 | Blocked | F_005
| TC_F_AMPC_02 | NegativePasswordChange1 |  | Dan | 2019-11-14 | Blocked | F_005
| TC_F_AMPC_03 | NegativePasswordChange2 |  | Dan | 2019-11-14 | Blocked | F_005
| TC_F_AMTR_01 | PositiveAddTravel |  | Dan | 2019-11-14 | Blocked | F_005
| TC_F_AMTR_02 | PositiveAddTravel |  | Dan | 2019-11-14 | Blocked | F_005
| TC_F_AMTR_03 | NegativeAddTravel |  | Dan | 2019-11-14 | Blocked | F_005
| TC_F_AMTR_04 | NegativeAddTravel |  | Dan | 2019-11-14 | Blocked | F_005
| TC_F_AMTR_05 | NegativeAddTravel |  | Dan | 2019-11-14 | Blocked | F_005
| TC_F_AMTR_06 | NegativeAddTravel |  | Dan | 2019-11-14 | Blocked | F_005
| TC_F_AMTR_07 | NegativeAddTravel |  | Dan | 2019-11-14 | Blocked | F_005
| TC_F_AMTR_08 | NegativeAddTravel |  | Dan | 2019-11-14 | Blocked | F_005
| TC_F_AMTR_09 | NegativeAddTravel |  | Dan | 2019-11-14 | Blocked | F_005
| TC_F_AMTR_10 | NegativeAddTravel |  | Dan | 2019-11-14 | Blocked | F_005
| TC_F_AMTR_11 | NegativeAddTravel |  | Dan | 2019-11-14 | Blocked | F_005
| TC_F_AMTR_12 | NegativeAddTravel |  | Dan | 2019-11-14 | Blocked | F_005
| TC_F_AMTR_13 | PositiveDeleteTravel |  | Dan | 2019-11-14 | Blocked | F_005
| TC_F_AMTR_14 | NegativeDeleteTravel1 |  | Dan | 2019-11-14 | Blocked | F_005
| TC_F_AMTR_15 | NegativeDeleteTravel2 |  | Dan | 2019-11-14 | Blocked | F_005
| TC_F_AMR_01 | PositiveAddRoute |  | Dan | 2019-11-14 | Blocked | F_005
| TC_F_AMR_02 | PositiveAddRoute |  | Dan | 2019-11-14 | Blocked | F_005
| TC_F_AMR_03 | NegativeAddRoute |  | Dan | 2019-11-14 | Blocked | F_005
| TC_F_AMR_04 | NegativeAddRoute |  | Dan | 2019-11-14 | Blocked | F_005
| TC_F_AMR_05 | NegativeAddRoute |  | Dan | 2019-11-14 | Blocked | F_005
| TC_F_AMR_06 | NegativeAddRoute |  | Dan | 2019-11-14 | Blocked | F_005
| TC_F_AMR_07 | NegativeAddRoute |  | Dan | 2019-11-14 | Blocked | F_005
| TC_F_AMR_08 | NegativeAddRoute |  | Dan | 2019-11-14 | Blocked | F_005
| TC_F_AMR_09 | NegativeAddRoute |  | Dan | 2019-11-14 | Blocked | F_005
| TC_F_AMR_10 | NegativeAddRoute |  | Dan | 2019-11-14 | Blocked | F_005
| TC_F_AMR_11 | NegativeAddRoute |  | Dan | 2019-11-14 | Blocked | F_005
| TC_F_AMR_12 | NegativeAddRoute |  | Dan | 2019-11-14 | Blocked | F_005
| TC_F_AMR_13 | NegativeAddRoute |  | Dan | 2019-11-14 | Blocked | F_005
| TC_F_AMR_14 | NegativeAddRoute |  | Dan | 2019-11-14 | Blocked | F_005
| TC_F_AMR_15 | NegativeAddRoute |  | Dan | 2019-11-14 | Blocked | F_005
| TC_F_AMR_16 | NegativeAddRoute |  | Dan | 2019-11-14 | Blocked | F_005
| TC_F_AMR_17 | NegativeAddRoute |  | Dan | 2019-11-14 | Blocked | F_005
| TC_F_AMR_18 | NegativeAddRoute |  | Dan | 2019-11-14 | Blocked | F_005
| TC_F_AMR_19 | NegativeAddRoute |  | Dan | 2019-11-14 | Blocked | F_005
| TC_F_AMR_20 | NegativeAddRoute |  | Dan | 2019-11-14 | Blocked | F_005
| TC_F_AMR_21 | NegativeAddRoute |  | Dan | 2019-11-14 | Blocked | F_005
| TC_F_AMR_22 | NegativeAddRoute |  | Dan | 2019-11-14 | Blocked | F_005
| TC_F_AMR_23 | PositiveDeleteRoute |  | Dan | 2019-11-14 | Blocked | F_005
| TC_F_AMR_24 | NegativeDeleteRoute1 |  | Dan | 2019-11-14 | Blocked | F_005
| TC_F_AMR_25 | NegativeDeleteRoute2 |  | Dan | 2019-11-14 | Blocked | F_005
Usability Test Cases
User Module | TC_U_UL_01 | EfficiencyLoginTest |  | Ralph | 2019-11-18 | Blocked | F_001: Login functions not working | High | Open
| TC_U_UL_02 | EffectivenessLoginTest |  | Ralph | 2019-11-18 | Blocked | F_001 | High | Open
| TC_U_UL_03 | SatisfactionLoginTest |  | Ralph | 2019-11-18 | Blocked | F_001 | High | Open
| TC_U_UL_04 | AccessibilityLoginTest |  | Ralph | 2019-11-18 | Blocked | F_001 | High | Open
Reservations Module | TC_U_BT_01 | EfficiencyBookTicketTest |  | Ralph | 2019-11-18 | Blocked | F_003: Can't select date and "Check Availability" button doesn't work | High | Open
| TC_U_BT_02 | EffectivenessBookTicketTest |  | Ralph | 2019-11-18 | Blocked | F_003 | High | Open
| TC_U_BT_03 | SatisfactionBookTicketTes |  | Ralph | 2019-11-18 | Blocked | F_003 | High | Open
| TC_U_BT_04 | AccessibilityBookTicketTes |  | Ralph | 2019-11-18 | Pass
| TC_U_CT_01 | EfficiencyCancelTickets |  | Ralph | 2019-11-18 | Blocked | F_004: "Cancel" button after entering proper ID does not work | Medium | Open
| TC_U_CT_02 | EffectivenessCancelTickets |  | Ralph | 2019-11-18 | Blocked | F_004 | Medium | Open
| TC_U_CT_03 | SatisfactionCancelTickets |  | Ralph | 2019-11-18 | Blocked | F_004 | Medium | Open
| TC_U_CT_04 | AccessibilityCancelTickets |  | Ralph | 2019-11-18 | Pass
Testimonials Module | TC_U_GT_01 | EfficiencyGiveTestimonials |  | Ralph | 2019-11-18 | Pass 10/10 able to give testimonial within 1:20 minutes
| TC_U_GT_02 | EffectivenessGiveTestimonials |  | Ralph | 2019-11-18 | Pass 10/10 able to give testimonial successfully
| TC_U_GT_03 | SatisfactionGiveTestimonials |  | Ralph | 2019-11-18 | Pass 10/10 rate the testimonial page as better
| TC_U_GT_04 | AccessibilityGiveTestimonials |  | Ralph | 2019-11-18 | Pass 10/10 able to
| TC_U_VT_01 | EfficiencyViewTestimonials |  | Ralph | 2019-11-18 | Pass 10/10 able to view testimonial within 3 second
| TC_U_VT_02 | EffectivenessViewTestimonials |  | Ralph | 2019-11-18 | Pass 10/10 able to give testimonial within 1 second
| TC_U_VT_03 | SatisfactionViewTestimonials |  | Ralph | 2019-11-18 | Pass 10/10 rate the view testimonials as good
| TC_U_VT_04 | AccessibilityViewTestimonials |  | Ralph | 2019-11-18 | Fail 10/10 can't view testimonials using navigation buttons | U_001 | Low | assigned
Routes Module | TC_U_VR_01 | EfficiencyViewRoutes |  | Ralph | 2019-11-18 | Pass 10/10 able to give testimonial within 1 second
| TC_U_VR_02 | EffectivenessViewRoutes |  | Ralph | 2019-11-18 | Pass 10/10 able to view routes successfully
| TC_U_VR_03 | SatisfactionViewRoutes |  | Ralph | 2019-11-18 | Fail 4/10 rate the view route as good | U_003 | Medium | Assigned
| TC_U_VR_04 | AccessibilityViewRoutes |  | Ralph | 2019-11-18 | Fail 10/10 can't navatigate view route page using navigation button | U_002 | Medium | assigned
Security Test Cases
Abuse Cases Module | TC_S_SQL_01 | DataEntryFieldSQLInjection |  | Francisco | 2019-11-17 | Blocked | F_001 | 1- Medium | open
| TC_S_SQL_02 | DataEntryFieldSQLInjection |  | Francisco | 2019-11-17 | Blocked | F_001
| TC_S_SQL_03 | DataEntryFieldSQLInjection |  | Francisco | 2019-11-17 | Blocked | F_001
| TC_S_SQL_06 | DataEntryFieldSQLInjection |  | Francisco | 2019-11-17 | Blocked | F_001 | 1- Medium | open
| TC_S_SQL_07 | DataEntryFieldSQLInjection |  | Francisco | 2019-11-17 | Blocked | F_001 | 1- Medium | Open
| TC_S_SQL_08 | DataEntryFieldSQLInjection |  | Francisco | 2019-11-17 | Blocked | F_001 | 1- Medium | Open
| TC_S_SQL_09 | DataEntryFieldSQLInjection |  | Francisco | 2019-11-17 | Blocked | F_001 | 1- Medium | Open
| TC_S_NS_01 | LoginNetworkSniffing |  | Francisco | 2019-11-17 | Blocked | F_001 | 1- High | Open
| TC_S_NS_02 | BookTicketsNetworkSniffing |  | Francisco | 2019-11-17 | Blocked | F_003
| TC_S_NS_03 | PaymentNetworkSniffing |  | Francisco | 2019-11-17 | Blocked | F_003
| TC_S_DDOS | DistributedDenialofServiceAttack |  | Francisco | 2019-11-17 | Pass |  | 1-High | Close
Performance Test Cases
| TC_P_LD_01 | ClickLoad test |  | Rose | 2019-11-12 | PASS
| TC_P_LD_02 | LoginLoad Test |  | Rose | 2019-11-12 | BLOCKED | F_001 | High | Open
| TC_P_LD_03 | BookTicketsLoadTest |  | Rose | 2019-11-13 | BLOCKED | F_003 | High | Open
| TC_P_LD_04 | UserGiveTestimonialLoadTest |  | Rose | 2019-11-13 | PASS
| TC_P_LD_05 | StressLoadClickTest |  | Rose | 2019-11-13 | PASS
| TC_P_LD_06 | RampUpClickLoadTest |  | Rose | 2019-11-13 | PASS
| TC_P_LD_07 | RampDownClickLoadTest |  | Rose | 2019-11-14 | PASS
| TC_P_V_1 | AddUserVolumeTest |  | Rose | 2019-11-14 | BLOCKED | F_005 | High | Open
| TC_P_V_2 | AddRouteVolumeTest |  | Rose | 2019-11-14 | BLOCKED | F_005 | High | Open
| TC_P_SPD_01 | LoginSpeedTest |  | Rose | 2019-11-12 | BLOCKED | F_001 | High | Open
| TC_P_SPD_02 | BookTicketsSpeedTest |  | Rose | 2019-11-13 | BLOCKED | F_003 | Medium | Open
| TC_P_SPD_03 | BookingConfirmationSpeedTest |  | Rose | 2019-11-13 | BLOCKED | F_003 | Medium | Open
| TC_P_SPD_04 | CancelTicketsSpeedTest |  | Rose | 2019-11-15 | BLOCKED | F_004 | High | Open
| TC_P_SPD_05 | CancelConfirmationSpeedTest |  | Rose | 2019-11-15 | BLOCKED | F_004 | High | Open
| TC_P_SPD_06 | GiveTestimonialSpeedTest |  | Rose | 2019-11-15 | PASS
Compatibility Test Cases
| TC_C_BRCV_01 | ChromeVersion 78.0.3904.70CompatibilityTest |  | Lyan | 2019-11-12 | Pass
| TC_C_BRCV_02 | ChromeVersion 77.0.3865.90CompatibilityTest |  | Lyan | 2019-11-12 | Pass
| TC_C_BRCV_03 | ChromeVersion74.0.3729.112CompatibilityTests |  | Lyan | 2019-11-12 | Pass
| TC_C_BRFFV_01 | FirefoxVersion70.0CompatibilityTest |  | Lyan | 2019-11-12 | Pass
| TC_C_BRFFV_02 | FirefoxVersion69.0.3.0CompatibilityTest |  | Lyan | 2019-11-12 | Pass
| TC_C_BRFFV_03 | FirefoxVersion64.0.2.0CompatibilityTest |  | Lyan | 2019-11-12 | Pass
| TC_C_BRFFV_04 | FirefoxVersion68.2..0CompatibilityTest |  | Lyan | 2019-11-12 | Pass
| TC_C_BRSV_01 | SafariForWindows10CompatibilityTest |  | Lyan | 2019-11-12 | Pass
| TC_C_BRSV_02 | SafariForWindows10V5.34.54.16CompatibilityTest |  | Lyan | 2019-11-12 | Pass
| TC_C_BRSV_03 | SafariForWindows10V5.1.1CompatibilityTest |  | Lyan | 2019-11-12 | Pass
| TC_C_BRSV_04 | SafariForWindows10V4.03CompatibilityTest |  | Lyan | 2019-11-12 | Fail | Comp_001 | High
| TC_C_BRIEV_01 | InternetExplorerV11CompatibilityTest |  | Lyan | 2019-11-12 | Pass
| TC_C_BRIEV_02 | InternetExplorerV8CompatibilityTest |  | Lyan | 2019-11-12 | Fail | Comp_002 | High
Design Test Cases
Testimonials Module | TC_D_GT_01 | GiveTestimonialsFontSize |  | Anand | 2019-11-12 | Fail | D_001 | Medium | open
| TC_D_GT_02 | GiveTestimonialsFontType |  | Anand | 2019-11-12 | Pass
| TC_D_GT_03 | GiveTestimonialsFontColor |  | Anand | 2019-11-12 | Pass
| TC_D_GT_04 | GiveTestimonialsPageColor |  | Anand | 2019-11-12 | Pass
| TC_D_GT_05 | GiveTestimonialsBackgroundColor |  | Anand | 2019-11-12 | Fail | D_002 | Medium | open
| TC_D_GT_06 | GiveTestimonialsScrollbarPresent |  | Anand | 2019-11-12 | Pass
| TC_D_VT_01 | ViewTestimonialsFontSize |  | Anand | 2019-11-13 | Pass
| TC_D_VT_02 | ViewTestimonialsFontType |  | Anand | 2019-11-13 | Pass
| TC_D_VT_03 | ViewTestimonialsFontColor |  | Anand | 2019-11-13 | Pass
| TC_D_VT_04 | ViewTestimonialsPageColor |  | Anand | 2019-11-13 | Pass
| TC_D_VT_05 | ViewTestimonialsBackgroundColor |  | Anand | 2019-11-13 | Pass
| TC_D_VT_06 | ViewTestimonialsQuantity |  | Anand | 2019-11-13 | Pass | D_003 | High | open
| TC_D_VT_07 | ViewTestimonialsTime |  | Anand | 2019-11-13 | Pass
| TC_D_VT_08 | ViewTestimonialsOrder |  | Anand | 2019-11-13 | Pass
User Module | TC_D_UL_01 | UserLoginButton |  | Anand | 2019-11-15 | Pass
| TC_D_UL_02 | UserLoginPage |  | Anand | 2019-11-15 | Pass
| TC_D_UL_03 | UserLoginSubmitButton |  | Anand | 2019-11-15 | Pass
| TC_D_UL_04 | UserLoginPasswordHidden |  | Anand | 2019-11-15 | Pass
| TC_D_UL_05 | UserLogoutButton |  | Anand | 2019-11-15 | Fail | D_004 | High | Open
| TC_D_UL_06 | UserLogoutButton2 |  | Anand | 2019-11-15 | Fail | D_005 | High | Open
Routes Module | TC_D_VR_01 | ViewRoutesButton |  | Anand | 2019-11-16 | Pass
| TC_D_VR_02 | ViewRoutesButton2 |  | Anand | 2019-11-16 | Pass
| TC_D_VR_03 | ViewRoutesQuantity |  | Anand | 2019-11-16 | Fail | D_006 | High | Open
| TC_D_VR_04 | ViewRouteOrganization |  | Anand | 2019-11-16 | Pass
| TC_D_VR_05 | ViewRoutesShowMoreButton |  | Anand | 2019-11-16 | Fail | D_007 | High | Open
| TC_D_VR_06 | ViewRoutesDetails |  | Anand | 2019-11-16 | Pass
| TC_D_VR_07 | ViewRouteInfoButton |  | Anand | 2019-11-16 | Pass
| TC_D_VPP_01 | ViewPickUpPointsWindow |  | Anand | 2019-11-17 | Pass
| TC_D_VPP_02 | ViewPickUpPointsQuantity |  | Anand | 2019-11-17 | Pass
| TC_D_VPP_03 | ViewPickUpPointsFontSize |  | Anand | 2019-11-17 | Fail | D_008 | Medium | Open
| TC_D_VPP_04 | ViewPickUpPointsBackgroundColor |  | Anand | 2019-11-17 | Fail | D_009 | Medium | Open
Reservations Module | TC_D_BT_01 | BookTicketsButton |  | Anand | 2019-11-18 | Pass
| TC_D_BT_02 | BookTicketsButton |  | Anand | 2019-11-18 | Pass
| TC_D_BT_03 | BookTicketsPage |  | Anand | 2019-11-18 | Pass
| TC_D_BT_04 | BookTicketsPageColor |  | Anand | 2019-11-18 | Pass
| TC_D_BT_05 | BookTicketsPageEntryFieldsColor |  | Anand | 2019-11-18 | Fail | D_010 | Medium | Open
| TC_D_BT_06 | BookTicketsPageCheckAvailabilityButton |  | Anand | 2019-11-18 | Pass
| TC_D_BT_07 | BookTicketsPageCheckAvailabilityButton2 |  | Anand | 2019-11-18 | Pass
| TC_D_BT_08 | BookTicketsPageProceedWithPurchaseButton |  | Anand | 2019-11-18 | Pass
| TC_D_BT_09 | BookTicketsPageProceedWithPurchaseButton |  | Anand | 2019-11-18 | Pass
| TC_D_CT_01 | CancelTicketsButton |  | Anand | 2019-11-18 | Pass
| TC_D_CT_02 | CancelTicketsButton2 |  | Anand | 2019-11-18 | Pass
| TC_D_CT_03 | CancelTicketsPageColor |  | Anand | 2019-11-18 | Pass
| TC_D_CT_04 | CancelTicketsTicketIDEntryField |  | Anand | 2019-11-18 | Pass
| TC_D_CT_05 | CancelTicketsTicketIDEntryFieldColor |  | Anand | 2019-11-18 | Pass
| TC_D_CT_06 | CancelTicketButton |  | Anand | 2019-11-18 | Pass
Admin Module | TC_D_AM_01 | AdminLoginButton |  | Anand | 2019-11-18 | Pass
| TC_D_AM_02 | AdminLoginButton1 |  | Anand | 2019-11-18 | Pass
| TC_D_AM_03 | AdminLoginPage |  | Anand | 2019-11-18 | Pass
| TC_D_AM_04 | AdminLoginSubmitButton |  | Anand | 2019-11-18 | Pass
| TC_D_AM_05 | AdminLoginPageColor |  | Anand | 2019-11-18 | Pass
| TC_D_AM_06 | AdminLoginEntryFieldsColor |  | Anand | 2019-11-18 | Pass
| TC_D_AM_07 | AdminPage |  | Anand | 2019-11-18 | blocked
| TC_D_AM_08 | AdminSubPagesDetails |  | Anand | 2019-11-18 | blocked
Note on J1: Author: Open, Assigned, Resolved

## Detailed Status - Phase 2
Module | Test Case ID | Test Case | Complexity | Responsible tester | Date of Execution(Can be past, present or future date) | Status(Pass/Fail/blocked/not executed) | Defect ID- Brief description | Severity | Status
Functional Test Cases
User Module | TC_F_UL_01 | PositiveUserLogin |  | Mrinal | 2019-11-19 | Fail | F_001: Login button takes user directly to main page. Never prompted for credentials | High | Open
| TC_F_UL_02 | NegativeUserLogin |  | Mrinal | 2019-11-19 | Fail | F_001 | High | Open
| TC_F_UL_03 | NegativeUserLogin |  | Mrinal | 2019-11-19 | Fail | F_001 | High | Open
| TC_F_UL_04 | NegativeUserLogin |  | Mrinal | 2019-11-19 | Fail | F_001 | High | Open
| TC_F_UL_05 | ExceptionUserLogin |  | Mrinal | 2019-11-19 | Fail | F_001 | High | Open
| TC_F_UL_06 | PositiveUserLogout |  | Mrinal | 2019-11-19 | Blocked | F_001
| TC_F_UL_07 | NegativeUserLogout |  | Mrinal | 2019-11-19 | Blocked | F_001
| TC_F_UL_08 | NegativeUserLogout |  | Mrinal | 2019-11-19 | Blocked | F_001
| TC_F_UL_09 | ExceptionUserLogout |  | Mrinal | 2019-11-19 | Blocked | F_001
Routes Module | TC_F_VR_01 | PositiveViewRoute |  | Mrinal | 2019-11-20 | Pass
| TC_F_VR_02 | NegativeViewRoute |  | Mrinal | 2019-11-20 | Pass
| TC_F_VR_03 | ExceptionViewRoute |  | Mrinal | 2019-11-20 | Pass
| TC_F_VPP_01 | PositiveViewPickupPoints |  | Mrinal | 2019-11-20 | Pass
| TC_F_VPP_02 | NegativeViewPickupPoints |  | Mrinal | 2019-11-20 | Pass
| TC_F_VPP_03 | ExceptionViewPickupPoints |  | Mrinal | 2019-11-20 | Pass
Travels Module | TC_F_VT_01 | PositiveViewTravel |  | Mrinal | 2019-11-20 | Fail | F_002: Travels Button not present on page. Can't even get to Travel Agency Section | Low | Assigned
| TC_F_VT_02 | NegativeViewTravel |  | Mrinal | 2019-11-20 | Fail | F_002 | Low | Assigned
| TC_F_VT_03 | ExceptionViewTravel |  | Mrinal | 2019-11-20 | Fail | F_002 | Low | Assigned
Testimonials Module | TC_F_TE_01 | PositiveGiveTestimonial |  | Mrinal | 2019-11-20 | Pass
| TC_F_TE_02 | NegativeGiveTestimonial |  | Mrinal | 2019-11-20 | Pass
| TC_F_TE_03 | NegativeGiveTestimonial |  | Mrinal | 2019-11-20 | Pass
| TC_F_TE_04 | PositiveViewTestimonials |  | Mrinal | 2019-11-20 | Pass
Reservations Module | TC_F_BT_01 | NegativeBookTickets1 |  | Dan | 2019-11-21 | Fail | F_003: Can't select date and "Check Availability" button doesn't work | High | Assigned
| TC_F_BT_02 | NegativeBookTickets2 |  | Dan | 2019-11-21 | Fail | F_003 | High | Assigned
| TC_F_BT_03 | NegativeBookTickets3 |  | Dan | 2019-11-21 | Fail | F_003 | High | Assigned
| TC_F_BT_04 | NegativeBookTickets4 |  | Dan | 2019-11-21 | Fail | F_003 | High | Assigned
| TC_F_BT_05 | NegativeBookTickets5 |  | Dan | 2019-11-21 | Fail | F_003 | High | Assigned
| TC_F_BT_06 | NegativeBookTickets6 |  | Dan | 2019-11-21 | Fail | F_003 | High | Assigned
| TC_F_BT_07 | NegativeBookTickets7 |  | Dan | 2019-11-21 | Fail | F_003 | High | Assigned
| TC_F_BT_08 | PositiveBookTickets |  | Dan | 2019-11-21 | Fail | F_003 | High | Assigned
| TC_F_CT_01 | NegativeCancelTickets |  | Dan | 2019-11-21 | Pass
| TC_F_CT_02 | NegativeCancelTickets |  | Dan | 2019-11-21 | Pass
| TC_F_CT_03 | NegativeCancelTickets |  | Dan | 2019-11-21 | Pass
| TC_F_CT_04 | PositiveCancelTickets |  | Dan | 2019-11-21 | Fail | F_004: "Cancel" button after entering proper ID does not work | High | Assigned
Admin Module | TC_F_AML_01 | PositiveAdminLogin |  | Dan | 2019-11-23 | Fail | F_006: Admin login not checking credentials. Just letting anyone in | High | Assigned
| TC_F_AML_02 | NegativeAdminLogin |  | Dan | 2019-11-23 | Fail | F_006
| TC_F_AML_03 | NegativeAdminLogin |  | Dan | 2019-11-23 | Fail | F_006
| TC_F_AML_04 | NegativeAdminLogin |  | Dan | 2019-11-23 | Fail | F_006
| TC_F_AML_05 | NegativeAdminLogin |  | Dan | 2019-11-23 | Fail | F_006
| TC_F_AML_06 | PositiveAdminLogout |  | Dan | 2019-11-23 | Pass
| TC_F_AML_07 | NegativeAdminLogout |  | Dan | 2019-11-23 | Pass
| TC_F_AML_08 | NegativeAdminLogout |  | Dan | 2019-11-23 | Pass
| TC_F_AML_09 | ExceptionAdminLogout |  | Dan | 2019-11-23 | Pass
| TC_F_AML_10 | ResetAdminLogin |  | Dan | 2019-11-23 | Pass
| TC_F_AMUC_01 | NegativeUserCreation1 |  | Dan | 2019-11-23 | Fail | F_007: User Creation Menu not present | High | Assigned
| TC_F_AMUC_02 | NegativeUserCreation2 |  | Dan | 2019-11-23 | Fail | F_007 | High
| TC_F_AMUC_03 | NegativeUserCreation3 |  | Dan | 2019-11-23 | Fail | F_007 | High
| TC_F_AMUC_04 | NegativeUserCreation4 |  | Dan | 2019-11-23 | Fail | F_007 | High
| TC_F_AMUC_05 | NegativeUserCreation5 |  | Dan | 2019-11-23 | Fail | F_007 | High
| TC_F_AMUC_06 | NegativeUserCreation6 |  | Dan | 2019-11-23 | Fail | F_007 | High
| TC_F_AMUC_07 | NegativeUserCreation7 |  | Dan | 2019-11-23 | Fail | F_007 | High
| TC_F_AMUC_08 | NegativeUserCreation8 |  | Dan | 2019-11-23 | Fail | F_007 | High
| TC_F_AMUC_09 | NegativeUserCreation9 |  | Dan | 2019-11-23 | Fail | F_007 | High
| TC_F_AMUC_10 | NegativeUserCreation10 |  | Dan | 2019-11-23 | Fail | F_007 | High
| TC_F_AMUC_11 | NegativeUserCreation11 |  | Dan | 2019-11-23 | Fail | F_007 | High
| TC_F_AMUC_12 | NegativeUserCreation12 |  | Dan | 2019-11-23 | Fail | F_007 | High
| TC_F_AMUC_13 | PositiveUserCreation1 |  | Dan | 2019-11-23 | Fail | F_007 | High
| TC_F_AMUC_14 | PositiveUserCreation2 |  | Dan | 2019-11-23 | Fail | F_007 | High
| TC_F_AMDU_01 | PositiveUserDeactivation |  | Dan | 2019-11-24 | Blocked | F_007
| TC_F_AMDU_02 | NegativeUserDeactivation1 |  | Dan | 2019-11-24 | Blocked | F_007
| TC_F_AMDU_03 | NegativeUserDeactivation2 |  | Dan | 2019-11-24 | Blocked | F_007
| TC_F_AMPC_01 | PositivePasswordChange |  | Dan | 2019-11-24 | Blocked | F_007
| TC_F_AMPC_02 | NegativePasswordChange1 |  | Dan | 2019-11-24 | Blocked | F_007
| TC_F_AMPC_03 | NegativePasswordChange2 |  | Dan | 2019-11-24 | Blocked | F_007
| TC_F_AMTR_01 | PositiveAddTravel |  | Dan | 2019-11-24 | Pass
| TC_F_AMTR_02 | PositiveAddTravel |  | Dan | 2019-11-24 | Pass
| TC_F_AMTR_03 | NegativeAddTravel |  | Dan | 2019-11-24 | Pass
| TC_F_AMTR_04 | NegativeAddTravel |  | Dan | 2019-11-24 | Pass
| TC_F_AMTR_05 | NegativeAddTravel |  | Dan | 2019-11-24 | Pass
| TC_F_AMTR_06 | NegativeAddTravel |  | Dan | 2019-11-24 | Pass
| TC_F_AMTR_07 | NegativeAddTravel |  | Dan | 2019-11-24 | Pass
| TC_F_AMTR_08 | NegativeAddTravel |  | Dan | 2019-11-24 | Pass
| TC_F_AMTR_09 | NegativeAddTravel |  | Dan | 2019-11-24 | Pass
| TC_F_AMTR_10 | NegativeAddTravel |  | Dan | 2019-11-24 | Pass
| TC_F_AMTR_11 | NegativeAddTravel |  | Dan | 2019-11-24 | Pass
| TC_F_AMTR_12 | NegativeAddTravel |  | Dan | 2019-11-24 | Pass
| TC_F_AMTR_13 | PositiveDeleteTravel |  | Dan | 2019-11-24 | Fail | F_008: Can't delete travels "Java nullpointer exception" | High | Assigned
| TC_F_AMTR_14 | NegativeDeleteTravel1 |  | Dan | 2019-11-24 | Fail | F_008
| TC_F_AMTR_15 | NegativeDeleteTravel2 |  | Dan | 2019-11-24 | Fail | F_008
| TC_F_AMR_01 | PositiveAddRoute |  | Dan | 2019-11-25 | Fail | F_009: Add route not functional: Can't enter date or select Travel Agency and Bus IDs
| TC_F_AMR_02 | PositiveAddRoute |  | Dan | 2019-11-25 | Fail | F_009
| TC_F_AMR_03 | NegativeAddRoute |  | Dan | 2019-11-25 | Fail | F_009
| TC_F_AMR_04 | NegativeAddRoute |  | Dan | 2019-11-25 | Fail | F_009
| TC_F_AMR_05 | NegativeAddRoute |  | Dan | 2019-11-25 | Fail | F_009
| TC_F_AMR_06 | NegativeAddRoute |  | Dan | 2019-11-25 | Fail | F_009
| TC_F_AMR_07 | NegativeAddRoute |  | Dan | 2019-11-25 | Fail | F_009
| TC_F_AMR_08 | NegativeAddRoute |  | Dan | 2019-11-25 | Fail | F_009
| TC_F_AMR_09 | NegativeAddRoute |  | Dan | 2019-11-25 | Fail | F_009
| TC_F_AMR_10 | NegativeAddRoute |  | Dan | 2019-11-25 | Fail | F_009
| TC_F_AMR_11 | NegativeAddRoute |  | Dan | 2019-11-25 | Fail | F_009
| TC_F_AMR_12 | NegativeAddRoute |  | Dan | 2019-11-25 | Fail | F_009
| TC_F_AMR_13 | NegativeAddRoute |  | Dan | 2019-11-25 | Fail | F_009
| TC_F_AMR_14 | NegativeAddRoute |  | Dan | 2019-11-25 | Fail | F_009
| TC_F_AMR_15 | NegativeAddRoute |  | Dan | 2019-11-25 | Fail | F_009
| TC_F_AMR_16 | NegativeAddRoute |  | Dan | 2019-11-25 | Fail | F_009
| TC_F_AMR_17 | NegativeAddRoute |  | Dan | 2019-11-25 | Fail | F_009
| TC_F_AMR_18 | NegativeAddRoute |  | Dan | 2019-11-25 | Fail | F_009
| TC_F_AMR_19 | NegativeAddRoute |  | Dan | 2019-11-25 | Fail | F_009
| TC_F_AMR_20 | NegativeAddRoute |  | Dan | 2019-11-25 | Fail | F_009
| TC_F_AMR_21 | NegativeAddRoute |  | Dan | 2019-11-25 | Fail | F_009
| TC_F_AMR_22 | NegativeAddRoute |  | Dan | 2019-11-25 | Fail | F_009
| TC_F_AMR_23 | PositiveDeleteRoute |  | Dan | 2019-11-25 | Fail | F_0010: Can't delete routes: null.pointer.exception
| TC_F_AMR_24 | NegativeDeleteRoute1 |  | Dan | 2019-11-25 | Fail | F_0010
| TC_F_AMR_25 | NegativeDeleteRoute2 |  | Dan | 2019-11-25 | Fail | F_0010
Usability Test Cases
User Module | TC_U_UL_01 | EfficiencyLoginTest |  | Ralph | 2019-11-23 | Blocked | F_001: Login functions not working | High | Open
| TC_U_UL_02 | EffectivenessLoginTest |  | Ralph | 2019-11-23 | Blocked | F_001 | High | Open
| TC_U_UL_03 | SatisfactionLoginTest |  | Ralph | 2019-11-23 | Blocked | F_001 | High | Open
| TC_U_UL_04 | AccessibilityLoginTest |  | Ralph | 2019-11-23 | Blocked | F_001 | High | Open
Reservations Module | TC_U_BT_01 | EfficiencyBookTicketTest |  | Ralph | 2019-11-23 | Blocked | F_003: Can't select date and "Check Availability" button doesn't work | High | Open
| TC_U_BT_02 | EffectivenessBookTicketTest |  | Ralph | 2019-11-23 | Blocked | F_003 | High | Open
| TC_U_BT_03 | SatisfactionBookTicketTes |  | Ralph | 2019-11-23 | Blocked | F_003 | High | Open
| TC_U_BT_04 | AccessibilityBookTicketTes |  | Ralph | 2019-11-23 | Pass
| TC_U_CT_01 | EfficiencyCancelTickets |  | Ralph | 2019-11-23 | Blocked | F_004: "Cancel" button after entering proper ID does not work | Medium | Open
| TC_U_CT_02 | EffectivenessCancelTickets |  | Ralph | 2019-11-23 | Blocked | F_004 | Medium | Open
| TC_U_CT_03 | SatisfactionCancelTickets |  | Ralph | 2019-11-23 | Blocked | F_004 | Medium | Open
| TC_U_CT_04 | AccessibilityCancelTickets |  | Ralph | 2019-11-23 | Pass
Testimonials Module | TC_U_GT_01 | EfficiencyGiveTestimonials |  | Ralph | 2019-11-23 | Pass 10/10 able to give testimonial within 1:20 minutes
| TC_U_GT_02 | EffectivenessGiveTestimonials |  | Ralph | 2019-11-23 | Pass 10/10 able to give testimonial successfully
| TC_U_GT_03 | SatisfactionGiveTestimonials |  | Ralph | 2019-11-23 | Pass 10/10 rate the testimonial page as better
| TC_U_GT_04 | AccessibilityGiveTestimonials |  | Ralph | 2019-11-23 | Pass 10/10 able to
| TC_U_VT_01 | EfficiencyViewTestimonials |  | Ralph | 2019-11-23 | Pass 10/10 able to view testimonial within 3 second
| TC_U_VT_02 | EffectivenessViewTestimonials |  | Ralph | 2019-11-23 | Pass 10/10 able to give testimonial within 1 second
| TC_U_VT_03 | SatisfactionViewTestimonials |  | Ralph | 2019-11-23 | Pass 10/10 rate the view testimonials as good
| TC_U_VT_04 | AccessibilityViewTestimonials |  | Ralph | 2019-11-23 | Fail 10/10 can't view testimonials using navigation buttons | U_001 | Low | assigned
Routes Module | TC_U_VR_01 | EfficiencyViewRoutes |  | Ralph | 2019-11-23 | Pass 10/10 able to give testimonial within 1 second
| TC_U_VR_02 | EffectivenessViewRoutes |  | Ralph | 2019-11-23 | Pass 10/10 able to view routes successfully
| TC_U_VR_03 | SatisfactionViewRoutes |  | Ralph | 2019-11-23 | Fail 4/10 rate the view route as good | U_003 | Medium | Assigned
| TC_U_VR_04 | AccessibilityViewRoutes |  | Ralph | 2019-11-23 | Fail 10/10 can't navatigate view route page using navigation button | U_002 | Medium | assigned
Security Test Cases
Abuse Cases Module | TC_S_SQL_01 | DataEntryFieldSQLInjection |  | Francisco | 2019-11-24 | Pass
| TC_S_SQL_02 | DataEntryFieldSQLInjection |  | Francisco | 2019-11-24 | Pass
| TC_S_SQL_03 | DataEntryFieldSQLInjection |  | Francisco | 2019-11-24 | Pass
| TC_S_SQL_06 | DataEntryFieldSQLInjection |  | Francisco | 2019-11-24 | Pass
| TC_S_SQL_07 | DataEntryFieldSQLInjection |  | Francisco | 2019-11-24 | fail | SEC_001 | 1- Medium | assigned
| TC_S_SQL_08 | DataEntryFieldSQLInjection |  | Francisco | 2019-11-24 | fail | SEC_002 | 1- Medium | assigned
| TC_S_SQL_09 | DataEntryFieldSQLInjection |  | Francisco | 2019-11-24 | fail | SEC_003 | 1- Medium | assigned
| TC_S_NS_01 | LoginNetworkSniffing |  | Francisco | 2019-11-24 | fail | SEC_001 | 1- High | assigned
| TC_S_NS_02 | BookTicketsNetworkSniffing |  | Francisco | 2019-11-24 | Pass | F_003 |  | assigned
| TC_S_NS_03 | PaymentNetworkSniffing |  | Francisco | 2019-11-24 | Pass | F_003 |  | assigned
| TC_S_DDOS | DistributedDenialofServiceAttack |  | Francisco | 2019-11-24 | Pass
Performance Test Cases
| TC_P_LD_01 | ClickLoad test |  | Rose | 2019-11-22 | PASS
| TC_P_LD_02 | LoginLoad Test |  | Rose | 2019-11-22 | BLOCKED | F_001 | High | Open
| TC_P_LD_03 | BookTicketsLoadTest |  | Rose | 2019-11-23 | BLOCKED | F_003 | High | Open
| TC_P_LD_04 | UserGiveTestimonialLoadTest |  | Rose | 2019-11-23 | PASS
| TC_P_LD_05 | StressLoadClickTest |  | Rose | 2019-11-23 | PASS
| TC_P_LD_06 | RampUpClickLoadTest |  | Rose | 2019-11-23 | PASS
| TC_P_LD_07 | RampDownClickLoadTest |  | Rose | 2019-11-24 | PASS
| TC_P_V_1 | AddUserVolumeTest |  | Rose | 2019-11-24 | BLOCKED | F_007 | High | Open
| TC_P_V_2 | AddRouteVolumeTest |  | Rose | 2019-11-24 | BLOCKED | F_007 | High | Open
| TC_P_SPD_01 | LoginSpeedTest |  | Rose | 2019-11-22 | BLOCKED | F_001 | High | Open
| TC_P_SPD_02 | BookTicketsSpeedTest |  | Rose | 2019-11-23 | BLOCKED | F_003 | Medium | Open
| TC_P_SPD_03 | BookingConfirmationSpeedTest |  | Rose | 2019-11-23 | BLOCKED | F_003 | Medium | Open
| TC_P_SPD_04 | CancelTicketsSpeedTest |  | Rose | 2019-11-25 | BLOCKED | F_004 | High | Open
| TC_P_SPD_05 | CancelConfirmationSpeedTest |  | Rose | 2019-11-25 | BLOCKED | F_004 | High | Open
| TC_P_SPD_06 | GiveTestimonialSpeedTest |  | Rose | 2019-11-25 | PASS
Compatibility Test Cases
| TC_C_BRCV_01 | ChromeVersion 78.0.3904.70CompatibilityTest |  | Lyan | 2019-11-22 | Pass
| TC_C_BRCV_02 | ChromeVersion 77.0.3865.90CompatibilityTest |  | Lyan | 2019-11-22 | Pass
| TC_C_BRCV_03 | ChromeVersion74.0.3729.112CompatibilityTests |  | Lyan | 2019-11-22 | Pass
| TC_C_BRFFV_01 | FirefoxVersion70.0CompatibilityTest |  | Lyan | 2019-11-22 | Pass
| TC_C_BRFFV_02 | FirefoxVersion69.0.3.0CompatibilityTest |  | Lyan | 2019-11-22 | Pass
| TC_C_BRFFV_03 | FirefoxVersion64.0.2.0CompatibilityTest |  | Lyan | 2019-11-22 | Pass
| TC_C_BRFFV_04 | FirefoxVersion68.2..0CompatibilityTest |  | Lyan | 2019-11-22 | Pass
| TC_C_BRSV_01 | SafariForWindows10CompatibilityTest |  | Lyan | 2019-11-22 | Pass
| TC_C_BRSV_02 | SafariForWindows10V5.34.54.16CompatibilityTest |  | Lyan | 2019-11-22 | Pass
| TC_C_BRSV_03 | SafariForWindows10V5.1.1CompatibilityTest |  | Lyan | 2019-11-22 | Pass
| TC_C_BRSV_04 | SafariForWindows10V4.03CompatibilityTest |  | Lyan | 2019-11-22 | Fail | Comp_001 | High
| TC_C_BRIEV_01 | InternetExplorerV11CompatibilityTest |  | Lyan | 2019-11-22 | Pass
| TC_C_BRIEV_02 | InternetExplorerV8CompatibilityTest |  | Lyan | 2019-11-22 | Fail | Comp_002 | High
Design Test Cases
Testimonials Module | TC_D_GT_01 | GiveTestimonialsFontSize |  | Anand | 2019-11-22 | Fail | D_001 | Medium | open
| TC_D_GT_02 | GiveTestimonialsFontType |  | Anand | 2019-11-22 | Pass
| TC_D_GT_03 | GiveTestimonialsFontColor |  | Anand | 2019-11-22 | Pass
| TC_D_GT_04 | GiveTestimonialsPageColor |  | Anand | 2019-11-22 | Pass
| TC_D_GT_05 | GiveTestimonialsBackgroundColor |  | Anand | 2019-11-22 | Fail | D_002 | Medium | open
| TC_D_GT_06 | GiveTestimonialsScrollbarPresent |  | Anand | 2019-11-22 | Pass
| TC_D_VT_01 | ViewTestimonialsFontSize |  | Anand | 2019-11-23 | Pass
| TC_D_VT_02 | ViewTestimonialsFontType |  | Anand | 2019-11-23 | Pass
| TC_D_VT_03 | ViewTestimonialsFontColor |  | Anand | 2019-11-23 | Pass
| TC_D_VT_04 | ViewTestimonialsPageColor |  | Anand | 2019-11-23 | Pass
| TC_D_VT_05 | ViewTestimonialsBackgroundColor |  | Anand | 2019-11-23 | Pass
| TC_D_VT_06 | ViewTestimonialsQuantity |  | Anand | 2019-11-23 | Pass | D_003 | High | open
| TC_D_VT_07 | ViewTestimonialsTime |  | Anand | 2019-11-23 | Pass
| TC_D_VT_08 | ViewTestimonialsOrder |  | Anand | 2019-11-23 | Pass
User Module | TC_D_UL_01 | UserLoginButton |  | Anand | 2019-11-25 | Pass
| TC_D_UL_02 | UserLoginPage |  | Anand | 2019-11-25 | Pass
| TC_D_UL_03 | UserLoginSubmitButton |  | Anand | 2019-11-25 | Pass
| TC_D_UL_04 | UserLoginPasswordHidden |  | Anand | 2019-11-25 | Pass
| TC_D_UL_05 | UserLogoutButton |  | Anand | 2019-11-25 | Fail | D_004 | High | Open
| TC_D_UL_06 | UserLogoutButton2 |  | Anand | 2019-11-25 | Fail | D_005 | High | Open
Routes Module | TC_D_VR_01 | ViewRoutesButton |  | Anand | 2019-11-26 | Pass
| TC_D_VR_02 | ViewRoutesButton2 |  | Anand | 2019-11-26 | Pass
| TC_D_VR_03 | ViewRoutesQuantity |  | Anand | 2019-11-26 | Fail | D_006 | High | Open
| TC_D_VR_04 | ViewRouteOrganization |  | Anand | 2019-11-26 | Pass
| TC_D_VR_05 | ViewRoutesShowMoreButton |  | Anand | 2019-11-26 | Fail | D_007 | High | Open
| TC_D_VR_06 | ViewRoutesDetails |  | Anand | 2019-11-26 | Pass
| TC_D_VR_07 | ViewRouteInfoButton |  | Anand | 2019-11-26 | Pass
| TC_D_VPP_01 | ViewPickUpPointsWindow |  | Anand | 2019-11-27 | Pass
| TC_D_VPP_02 | ViewPickUpPointsQuantity |  | Anand | 2019-11-27 | Pass
| TC_D_VPP_03 | ViewPickUpPointsFontSize |  | Anand | 2019-11-27 | Fail | D_008 | Medium | Open
| TC_D_VPP_04 | ViewPickUpPointsBackgroundColor |  | Anand | 2019-11-27 | Fail | D_009 | Medium | Open
Reservations Module | TC_D_BT_01 | BookTicketsButton |  | Anand | 2019-11-28 | Pass
| TC_D_BT_02 | BookTicketsButton |  | Anand | 2019-11-28 | Pass
| TC_D_BT_03 | BookTicketsPage |  | Anand | 2019-11-28 | Pass
| TC_D_BT_04 | BookTicketsPageColor |  | Anand | 2019-11-28 | Pass
| TC_D_BT_05 | BookTicketsPageEntryFieldsColor |  | Anand | 2019-11-28 | Fail | D_010 | Medium | Open
| TC_D_BT_06 | BookTicketsPageCheckAvailabilityButton |  | Anand | 2019-11-28 | Pass
| TC_D_BT_07 | BookTicketsPageCheckAvailabilityButton2 |  | Anand | 2019-11-28 | Pass
| TC_D_BT_08 | BookTicketsPageProceedWithPurchaseButton |  | Anand | 2019-11-28 | Pass
| TC_D_BT_09 | BookTicketsPageProceedWithPurchaseButton |  | Anand | 2019-11-28 | Pass
| TC_D_CT_01 | CancelTicketsButton |  | Anand | 2019-11-28 | Pass
| TC_D_CT_02 | CancelTicketsButton2 |  | Anand | 2019-11-28 | Pass
| TC_D_CT_03 | CancelTicketsPageColor |  | Anand | 2019-11-28 | Pass
| TC_D_CT_04 | CancelTicketsTicketIDEntryField |  | Anand | 2019-11-28 | Pass
| TC_D_CT_05 | CancelTicketsTicketIDEntryFieldColor |  | Anand | 2019-11-28 | Pass
| TC_D_CT_06 | CancelTicketButton |  | Anand | 2019-11-28 | Pass
Admin Module | TC_D_AM_01 | AdminLoginButton |  | Anand | 2019-11-28 | Pass
| TC_D_AM_02 | AdminLoginButton1 |  | Anand | 2019-11-28 | Pass
| TC_D_AM_03 | AdminLoginPage |  | Anand | 2019-11-28 | Pass
| TC_D_AM_04 | AdminLoginSubmitButton |  | Anand | 2019-11-28 | Pass
| TC_D_AM_05 | AdminLoginPageColor |  | Anand | 2019-11-28 | Pass
| TC_D_AM_06 | AdminLoginEntryFieldsColor |  | Anand | 2019-11-28 | Pass
| TC_D_AM_07 | AdminPage |  | Anand | 2019-11-28 | Pass
| TC_D_AM_08 | AdminSubPagesDetails |  | Anand | 2019-11-28 | Pass
Note on J1: Author: Open, Assigned, Resolved

## Defect Tracking Log
DEFECT TRACKING LOG
Project Name | Capstone
Program Manager | Kim Gariepy
Project Manager | Daniel Gilbert
Purpose: To ensure that the work product meets specifications for performance, defects must be tracked and fixed. These defects may arise from any Phase, but the majority will arise in the Testing Phase and must be properly captured and tracked through resolution. This form will allow documentation of test defects that must be corrected prior to project completion. Also, this form makes it easier to monitor status of the defect correction progress. This form may be used by any member of the software development team.
< Hover by the red triangle in the top left corner for more detail. Use the Instructions on the next tab to fill out fields.>
Defect No. | Date Created | Created By | Defect Description | Corresponding Test Case / Test Script ID | Steps to Reproduce | PM Process | Lifecycle Phase | Priority | Owner | Assigned Date | Estimated Time to Fix | Status | Resolution | Resolution Date | Actual Time to Fix | Root Cause | Status | Priority | PM | Lifecycle Phase
F_001 | 12-11-2019 | Mrinal | User login button takes User diectly to Welcome Page. User Credential fields never presented | TC_F_UL_01 --> TC_F_UL_09 TC_U_UL_01 --> TC_U_UL_04 TC_P_LD_02 TC_P_SPD_01 | 1. Navigate to website Home Page - localhost:8080/ewheelz 2. Click "User Login" button | Executing/Controlling | Testing | High | Mrinal | 12-11-2019 | 3 hrs | In Progress |  |  |  |  | New
F_002 | 12-11-2019 | Mrinal | Travel Agency Section not present on web page. No "Travels" button exists | TC_F_VT_01 --> TC_F_VT_03 | 1. Navigate to website Home Page - localhost:8080/ewheelz 2. Click "User Login" button 3. Check lefthand menu for "Travels" button which will not be there | Executing/Controlling | Testing | Low | Mrinal | 12-11-2019 | 1 hrs | In Progress |  |  |  |  | Under Review | High | Opportunity Assessment | Opportunity Assessment
F_003 | 13-11-2019 | Dan | Unable to enter date for Tickets and "Check Availability" button does not work | TC_F_BT_01 --> TC_F_BT_08 TC_U_BT_01 --> TC_U_BT_04 | 1. Navigate to website Home Page - localhost:8080/ewheelz 2. Click "User Login" button 3. Click "Book Tickets" button in lefthand menu 4. Enter ticket data, attempt to fill Date field and attempt to click "Check availability button | Executing/Controlling | Testing | High | Dan | 13-11-2019 | 5 hrs | In Progress |  |  |  |  | In Progress | Medium | Initiating | Concept
F_004 | 13-11-2019 | Dan | "Cancel" button after entering ticket selection does not work | TC_F_CT_04 | 1. Navigate to website Home Page - localhost:8080/ewheelz 2. Click "User Login" button 3. Click "Canel Tickets" button in lefthand menu 4. Enter ticket ID, click "Cancel Ticket" then on nect page click "Cancel | Executing/Controlling | Testing | High | Dan | 13-11-2019 | 2 hrs | In Progress |  |  |  |  | Completed | Low | Planning | Requirements
F_005 | 14-11-2019 | Dan | Admin login page completely non-functional | TC_F_AML_02 --> TC_F_AMR_25 TC_P_V_1 --> TC_P_V_2 | 1. Navigate to website Home Page - localhost:8080/ewheelz 2. Click "Admin Login" button 3. Enter Credentials 4. Click "Go" button (Which should be a "Submit" button) | Executing/Controlling | Testing | High | Dan | 13-11-2019 | 2 hrs | In Progress | Admin login funtional now, but not properly checking credentials. Let's anyone in | 19-11-2019 | 2 hrs | Wrong button for submission in place |  |  | Executing/Controlling | Design
F_006 | 19-11-2019 | Dan | Admin login letting not checking credentials | TC_F_AML_01 --> TC_F_AML_05 | 1. Navigate to website Home Page - localhost:8080/ewheelz 2. Click "Admin Login" button 3. Click "Submit" button | Executing/Controlling | Testing | High | Dan | 19-11-2019 | 3 hrs | In Progress
F_007 | 23-11-2019 | Dan | User Creation functionality not present in the Admin Page | TC_F_AMUC_01 --> TC_F_AMUC_05 TC_F_AMDU_01 --> TC_F_AMDU_03 | 1. Navigate to website Home Page - localhost:8080/ewheelz 2. Click "Admin Login" button 3. Click "Submit" button 4. Look for "Add User" button on Admin page | Executing/Controlling | Testing | High | Dan | 23-11-2019 | 3 hrs | In Progress
F_008 | 24-11-2019 | Dan | Can't delete travels: "java.lang.NullPointerException" | TC_F_AMTR_13 --> TC_F_AMTR_15 | 1. Navigate to website Home Page - localhost:8080/ewheelz 2. Click "Admin Login" button 3. Click "Submit" button 4. Click "Add Travel" 5. Enter properly formatted details for Travel 6. Click "Submit" | Executing/Controlling | Testing | High | Dan | 24-11-2019 | 3 hrs | In Progress
F_009 | 25-11-2019 | Dan | Can't add routes: Can select Travel or Bus IDs, can't select departure date | TC_F_AMR_1 --> TC_F_AMR_23 | 1. Navigate to website Home Page - localhost:8080/ewheelz 2. Click "Admin Login" button 3. Click "Submit" button 4. Click "Add Route" 5. Attempt to select Travel ID, Bus ID or departure date | Executing/Controlling | Testing | High | Dan | 25-11-2019 | 6 hrs | In Progress
F_0010 | 25-11-2019 | Dan | Can't delete routes: "java.lang.NullPointerException" | TC_F_AMR_23 --> TC_F_AMR_25 | 1. Navigate to website Home Page - localhost:8080/ewheelz 2. Click "Admin Login" button 3. Click "Submit" button 4. Click "Delete Route" 5. Select Route and click "Delete" | Executing/Controlling | Testing | High | Dan | 25-11-2019 | 3 hrs | In Progress
[19 empty] | Closing | Development
U_001 | 18-11-2019 | Ralph | Can't use accessibility controls to navigate through Testimonials. They just autoscroll | TC_U_VT_04 | 1. Navigate to website Home Page - localhost:8080/ewheelz 2. Click "User Login" button 3. Click "View Testimonials" button 4. Attempt to use "Tab" key to navigate through testimonials | Executing/Controlling | Testing | Medium | Ralph | 18-11-2019 | 21-11-2019 | In Progress | [7 empty] | Testing
U_002 | 18-11-2019 | Ralph | Can't use accessibility controls to navigate through Routes | TC_U_VR_04 | 1. Navigate to website Home Page - localhost:8080/ewheelz 2. Click "User Login" button 3. Click "View Routes" button 4. Attempt to Navigate through Route menues using "Tab" key | Executing/Controlling | Testing | Medium | Ralph | 18-11-2019 | 21-11-2019 | In Progress | [7 empty] | Documentation and Training
U_003 | 18-11-2019 | Ralph | View Routes usability experience sub par | TC_U_VR_04 | 1. Navigate to website Home Page - localhost:8080/ewheelz 2. Click "User Login" button 3. Click "View Routes" button 4. Compare View Routes User Interface with that of similar websites | Executing/Controlling | Testing | Medium | Ralph | 18-11-2019 | 21-11-2019 | In Progress | [7 empty] | Deployment
Post-Deployment
D_001 | 17-11-2019 | Anand | Front size of testimonials does not meet the requirments | TC_D_GT_01 | 1. Navigate to website Home Page - localhost:8080/ewheelz 2. Click "Testimonials" button | Executing/Controlling | Testing | Medium | Mrinal | 17-11-2019 | 1 hr | In Progress
D_002 | 17-11-2019 | Anand | Background colour does not meet the requirments | TC_D_GT_05 | 1. Navigate to website Home Page - localhost:8080/ewheelz 2. Click "Testimonials" button | Executing/Controlling | Testing | Medium | Mrinal | 17-11-2019 | 2hrs | In Progress
D_003 | 17-11-2019 | Anand | Testimonals displayed does not meet the reuirments. Only 13 testimonials are displayed instead of 15 testimonials. | TC_D_VT_06 | 1. Navigate to website Home Page - localhost:8080/ewheelz 2. Click " User Login" button | Executing/Controlling | Testing | Medium | Mrinal | 17-11-2019 | 1hr | In Progress
D_004 | 17-11-2019 | Anand | Logout out button is not present | TC_D_UL_05 | 1. Navigate to website Home Page - localhost:8080/ewheelz 2. Click " View Testimonials" button | Executing/Controlling | Testing | Medium | Mrinal | 17-11-2019 | 1hr | In Progress
D_005 | 17-11-2019 | Anand | Logout out button is not present | TC_D_UL_06 | 1. Navigate to website Home Page - localhost:8080/ewheelz 2. Click " User Login" button | Executing/Controlling | Testing | Medium | Mrinal | 17-11-2019 | 1hr | In Progress
D_006 | 17-11-2019 | Anand | Only 8 routes are displayed instead of 50 routes | TC_D_VR_03 | 1. Navigate to website Home Page - localhost:8080/ewheelz 2. Click " View Routes" button | Executing/Controlling | Testing | Medium | Mrinal | 17-11-2019 | 1hr | In Progress
D_007 | 17-11-2019 | Anand | view routes show more button is not shown | TC_D_VR_05 | 1. Navigate to website Home Page - localhost:8080/ewheelz 2. Click "view Routes " button | Executing/Controlling | Testing | Medium | Mrinal | 17-11-2019 | 1hr | In Progress
D_008 | 17-11-2019 | Anand | Front size does not meet the reuirments. It should be 11 instead it is 9. | TC_D_VPP_03 | 1. Navigate to website Home Page - localhost:8080/ewheelz 2. Click "view Routes " button | Executing/Controlling | Testing | Medium | Mrinal | 17-11-2019 | 2hrs | In Progress
D_009 | 11-21-19 | Anand | Background colour does not meet the reuirments it should be white instead it is purplish with light blue. | TC_D_VPP_04 | 1. Navigate to website Home Page - localhost:8080/ewheelz 2. Click "view Routes " button | Executing/Controlling | Testing | Medium | Mrinal | 17-11-2019 | 1hr | In Progress
D_010 | 11-21-19 | Anand | entry fields are white but the text colour is light blue. | TC_D_BT_05 | 1. Navigate to website Home Page - localhost:8080/ewheelz 2. Click " Book Tickets" button | Executing/Controlling | Testing | Medium | Mrinal | 17-11-2019 | 2hrs | In Progress
Comp_001 | 2019-11-21 | Lyan | Adobe Flash Player | TC_C_BRSV_04 | 1. Navigate to website Home Page - localhost:8080/ewheelz | Executing/Controlling | Testing | Low | Lyan | 15-11-2019 | 5 hrs | In Progress
Comp_002 | 2019-11-21 | Lyan | Adobe Flash Player | TC_C_BRIEV_02 | 1. Navigate to website Home Page - localhost:8080/ewheelz | Executing/Controlling | Testing | Low | Lyan | 15-11-2019 | 5 hrs | In Progress
SEC_001 | 2019-11-18 | Francisco | User Admin login button is not enable (defect web site) | TC_S_SQL_07 | 1. Navigate to http://localhost:8080/ewheelz/AdminLogin.html 2. inject command SQL text box user / password 3. command : Username: 'or'1'='1" 4. click button submit | Executing/Controlling | Testing | Medium | Francisco | 2019-11-18 | 2 weeks | Completed
SEC_002 | 2019-11-18 | Francisco | User Admin login button is not enable (defect web site) | TC_S_SQL_08 | 1. Navigate to http://localhost:8080/ewheelz/AdminLogin.html 2. inject command SQL text box user / password 3. command : Username: 'or'a'='a" 4. click button submit | Executing/Controlling | Testing | Medium | Francisco | 2019-11-18 | 2 weeks | Completed
SEC_003 | 2019-11-18 | Francisco | User Admin login button is not enable (defect web site) | TC_S_SQL_09 | 1. Navigate to http://localhost:8080/ewheelz/AdminLogin.html 2. inject command SQL text box user / password 3. command : Username: "Password:' or'1'='1--" 4. click button submit | Executing/Controlling | Testing | Medium | Francisco | 2019-11-18 | 2 weeks | Completed
Formulas:
Assigned Date = [Date Created]
Note on G10: Choose from the drop down box.
Note on H10: Choose from the drop down box.
Note on I10: Choose from the drop down list
Note on M10: Choose from the drop down list.

## Team Details
INFO6068 | Capstone Project
Team Name: | Team Pro-Test
Members: | Daniel Gilbert - Tester A
Mrinal Chopra - Tester B
Lyan Joy Limjap - Tester C
Francisco Gomez - Tester D
Ralph Anonuevo - Tester E
Rose Maria George - Tester F
Anand Karithadathil Baby - Tester G

## References - Performance
USER CLICK
USER LOGIN
ramp up
STRESSCLICK
give testimonial